## Sheet1
COST ESTIMATING WORKSHEET
Project Title: |  |  | Date Prepared:
Parametric Estimates
WBS ID | Cost Variable | Cost per Unit | Number of Units | Cost Estimate
Analogous Estimates
WBS ID | Previous Activity | Previous Cost | Current Activity | Multiplier | Cost Estimate
Three Point Estimates
WBS ID | Optimistic Cost | Most Likely Cost | Pessimistic Cost | Weighting Equation | Expected Cost Estimate

## Sheet2
Parametric Estimates
WBS ID | Effort Hours | Resource Quantity | % available | Performance factor | Duration Estimate
1.1 | 150 | 2 | 75% | 80% | 125
Analogous Estimates
WBS ID | Prior activity | Prior Variable | Duration | Current variable | Multiplier | Duration Estimate
1.1 | Build deck | 160 sq. ft. | 10 days | 200 sq. ft. | 1.25 | 12.5
Three Point Estimates
WBS ID | Optimistic estimate | Most likely estimate | Pessimistic estimate | Weighting factor | Expected Duration Estimate
1.1 | 20 | 25 | 36 | (o+4m+p)/6 | 26