## Sheet1
DURATION ESTIMATING WORKSHEET
Project Title: |  |  | Date Prepared:
Parametric Estimates
WBS ID | Effort Hours | Resource Quantity | % Available | Performance Factor | Duration Estimate
Analogous Estimates
WBS ID | Previous Activity | Previous Duration | Current Activity | Multiplier | Duration Estimate
Three Point Estimates
WBS ID | Optimistic Duration | Most Likely Duration | Pessimistic Duration | Weighting Equation | Expected Duration Estimate

## Sheet2
Parametric Estimates
WBS ID | Effort Hours | Resource Quantity | % available | Performance factor | Duration Estimate
1.1 | 150 | 2 | 75% | 80% | 125
Analogous Estimates
WBS ID | Prior activity | Prior Variable | Duration | Current variable | Multiplier | Duration Estimate
1.1 | Build deck | 160 sq. ft. | 10 days | 200 sq. ft. | 1.25 | 12.5
Three Point Estimates
WBS ID | Optimistic estimate | Most likely estimate | Pessimistic estimate | Weighting factor | Expected Duration Estimate
1.1 | 20 | 25 | 36 | (o+4m+p)/6 | 26